## Action Plan
Haverton Recruitment Action Plan
Yellow cell: enter your start date. Blue cells: update status, done date and evidence. Due dates and overdue flags calculate automatically.
Start date (day 1) |  | 2026-09-24 |  | Done | 0 of 36
|  |  |  | Overdue | 0
Day | Phase | Action | Deliverable | Owner | Due date | Status | Done date | Flag | Evidence kept where
1 | Week 1: Foundations | Confirm niche, roles and service area | Written service model | Suroj Aryal | 2026-09-24 | Not started |  | Due soon
2 | Week 1: Foundations | Confirm permanent first, temporary readiness in parallel | Business plan agreed | Suroj Aryal | 2026-09-25 | Not started |  | Due soon
3 | Week 1: Foundations | Add SIC code 78109 to the Companies House action list | Note for next confirmation statement | Suroj Aryal | 2026-09-26 | Not started |  | Due soon
4 | Week 1: Foundations | Open or confirm the business bank account for recruitment income | Account details for invoices | Suroj Aryal | 2026-09-27 | Not started |  | Due soon
5 | Week 1: Foundations | Choose an accountant and a payroll provider with recruitment experience | Payroll proposal | Suroj Aryal | 2026-09-28 | Not started |  | Due soon
6 | Week 1: Foundations | Get 2 to 3 insurance quotes using the Insurance Broker Brief | Insurance comparison | Suroj Aryal | 2026-09-29 | Not started |  | Due soon
7 | Week 1: Foundations | Buy professional indemnity insurance (employers’ liability before any temporary worker) | Insurance certificates | Suroj Aryal | 2026-09-30 | Not started |  | Due soon
8 | Week 1: Foundations | Confirm ICO fee is paid and publish the Recruitment Privacy Notice | ICO number; notice on website | Suroj Aryal | 2026-10-01 | Not started |  | Due soon
9 | Week 1: Foundations | Accept the Supabase data processing agreement; set own password; delete the setup token | Screenshot or note of acceptance | Suroj Aryal | 2026-10-02 | Not started
10 | Week 1: Foundations | Publish a Recruitment page on the website, separate from home care | Live page | Suroj Aryal | 2026-10-03 | Not started
11 | Week 2: Legal And Compliance | Solicitor review: Client Terms Of Business (permanent) | Signed-off terms | Suroj Aryal | 2026-10-04 | Not started
12 | Week 2: Legal And Compliance | Solicitor review: Client Terms For Temporary Supply | Signed-off draft (not in use yet) | Suroj Aryal | 2026-10-05 | Not started
13 | Week 2: Legal And Compliance | Solicitor review: Candidate Terms, Temporary Worker Terms and Key Information Document | Signed-off candidate pack | Suroj Aryal | 2026-10-06 | Not started
14 | Week 2: Legal And Compliance | Adopt the Candidate File Checklist and set up restricted folders | Folder structure | Suroj Aryal | 2026-10-07 | Not started
15 | Week 2: Legal And Compliance | Register with a DBS umbrella body | Account confirmed | Suroj Aryal | 2026-10-08 | Not started
16 | Week 2: Legal And Compliance | Start using the Interview Scoring Sheet for every interview | First completed sheets | Suroj Aryal | 2026-10-09 | Not started
17 | Week 2: Legal And Compliance | Confirm safeguarding, complaints and whistleblowing procedure (SOP 17) | Procedure read and dated | Suroj Aryal | 2026-10-10 | Not started
18 | Week 3: Market | Enter 150 local care providers in the Clients register | 150 client records | Suroj Aryal | 2026-10-11 | Not started
19 | Week 3: Market | Map decision-makers: owners, HR leads, Registered Managers | Contacts recorded | Suroj Aryal | 2026-10-12 | Not started
20 | Week 3: Market | Create LinkedIn company page and update founder profile | Live pages | Suroj Aryal | 2026-10-13 | Not started
21 | Week 3: Market | Start candidate sourcing: aim for 100 conversations this month | Candidates registered | Suroj Aryal | 2026-10-14 | Not started
22 | Week 3: Market | Screen the first 20 candidates with consent records | 20 screened candidates | Suroj Aryal | 2026-10-15 | Not started
23 | Week 3: Market | Client calling campaign: 30 conversations | Activity logged | Suroj Aryal | 2026-10-16 | Not started
24 | Week 3: Market | Send tailored introduction emails | Emails logged | Suroj Aryal | 2026-10-17 | Not started
25 | Week 3: Market | Book 5 discovery meetings | Meetings in diary | Suroj Aryal | 2026-10-18 | Not started
26 | Week 4: First Business | Win the first live permanent vacancy with signed terms | Signed terms and Vacancy Brief | Suroj Aryal | 2026-10-19 | Not started
27 | Week 4: First Business | Check temporary rates for each role in the Pricing Calculators | Rate card (not in use yet) | Suroj Aryal | 2026-10-20 | Not started
28 | Week 4: First Business | Credit-check possible temporary clients (no supply yet) | Approved client list and limits | Suroj Aryal | 2026-10-21 | Not started
29 | Week 4: First Business | Audit documents and systems; record it in the Audits register | Audit record | Suroj Aryal | 2026-10-22 | Not started
30 | Week 4: First Business | Review the pipeline and set the 90-day plan | Monthly report | Suroj Aryal | 2026-10-23 | Not started
45 | Temporary Staffing Readiness | Payroll provider set up; PAYE, pension and holiday pay tested | Test payroll run | Suroj Aryal | 2026-11-07 | Not started
50 | Temporary Staffing Readiness | Employers’ liability (at least £5 million) and temporary staffing cover in place | Certificates | Suroj Aryal | 2026-11-12 | Not started
55 | Temporary Staffing Readiness | 13-week cash-flow forecast and funding (for example invoice finance) agreed | Forecast and facility letter | Suroj Aryal | 2026-11-17 | Not started
60 | Temporary Staffing Readiness | Credit limits, weekly invoicing, 7-day terms and stop-supply rule agreed | Client credit file | Suroj Aryal | 2026-11-22 | Not started
75 | Temporary Staffing Readiness | Director signs every item in the Temp Go Live Gate | Gate showing GO | Suroj Aryal | 2026-12-07 | Not started
90 | Temporary Staffing Readiness | Pilot with 1 to 2 trusted clients, then audit after the first payroll | Pilot audit | Suroj Aryal | 2026-12-22 | Not started
Formulas:
Due date = C3+[Day]-1
Flag = IF(OR([Status]="Done",[Status]="Not needed"),"",IF([Due date]<TODAY(),"Overdue",IF([Due date]<=TODAY()+7,"Due soon","")))

## Weekly Routine
Weekly routine
Enter the number achieved each week. Targets from the founder launch rhythm.
Activity | Weekly target | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
Research target providers | 20
Tailored first emails | 10
Follow-up calls | 15
Discovery meetings | 3
Candidate screening conversations | 5
Consented submissions | 2