HAVERTON CARE LIMITED

Action Plan

Tick each box when done, write the date, and note where the evidence is

| How to use it | Write the start date below. Day numbers count from that date. The same plan is in Haverton Operations (Action Plan page), where due dates and overdue alerts are automatic. |
| --- | --- |
| Start date (day 1) |  |
| Owner | Suroj Aryal |

Legal requirement or good practice? Items that are a legal requirement say so in the Launch Checklist. Everything here is either needed to start lawfully or is recommended practice for a safe, well-run agency.

# Week 1: Foundations

| Day | Action | Deliverable | Done | Date done | Evidence kept where |
| --- | --- | --- | --- | --- | --- |
| 1 | Confirm niche, roles and service area | Written service model | ☐ |  |  |
| 2 | Confirm permanent first, temporary readiness in parallel | Business plan agreed | ☐ |  |  |
| 3 | Add SIC code 78109 to the Companies House action list | Note for next confirmation statement | ☐ |  |  |
| 4 | Open or confirm the business bank account for recruitment income | Account details for invoices | ☐ |  |  |
| 5 | Choose an accountant and a payroll provider with recruitment experience | Payroll proposal | ☐ |  |  |
| 6 | Get 2 to 3 insurance quotes using the Insurance Broker Brief | Insurance comparison | ☐ |  |  |
| 7 | Buy professional indemnity insurance (employers’ liability before any temporary worker) | Insurance certificates | ☐ |  |  |
| 8 | Confirm ICO fee is paid and publish the Recruitment Privacy Notice | ICO number; notice on website | ☐ |  |  |
| 9 | Accept the Supabase data processing agreement; set own password; delete the setup token | Screenshot or note of acceptance | ☐ |  |  |
| 10 | Publish a Recruitment page on the website, separate from home care | Live page | ☐ |  |  |

# Week 2: Legal And Compliance

| Day | Action | Deliverable | Done | Date done | Evidence kept where |
| --- | --- | --- | --- | --- | --- |
| 11 | Solicitor review: Client Terms Of Business (permanent) | Signed-off terms | ☐ |  |  |
| 12 | Solicitor review: Client Terms For Temporary Supply | Signed-off draft (not in use yet) | ☐ |  |  |
| 13 | Solicitor review: Candidate Terms, Temporary Worker Terms and Key Information Document | Signed-off candidate pack | ☐ |  |  |
| 14 | Adopt the Candidate File Checklist and set up restricted folders | Folder structure | ☐ |  |  |
| 15 | Register with a DBS umbrella body | Account confirmed | ☐ |  |  |
| 16 | Start using the Interview Scoring Sheet for every interview | First completed sheets | ☐ |  |  |
| 17 | Confirm safeguarding, complaints and whistleblowing procedure (SOP 17) | Procedure read and dated | ☐ |  |  |

# Week 3: Market

| Day | Action | Deliverable | Done | Date done | Evidence kept where |
| --- | --- | --- | --- | --- | --- |
| 18 | Enter 150 local care providers in the Clients register | 150 client records | ☐ |  |  |
| 19 | Map decision-makers: owners, HR leads, Registered Managers | Contacts recorded | ☐ |  |  |
| 20 | Create LinkedIn company page and update founder profile | Live pages | ☐ |  |  |
| 21 | Start candidate sourcing: aim for 100 conversations this month | Candidates registered | ☐ |  |  |
| 22 | Screen the first 20 candidates with consent records | 20 screened candidates | ☐ |  |  |
| 23 | Client calling campaign: 30 conversations | Activity logged | ☐ |  |  |
| 24 | Send tailored introduction emails | Emails logged | ☐ |  |  |
| 25 | Book 5 discovery meetings | Meetings in diary | ☐ |  |  |

# Week 4: First Business

| Day | Action | Deliverable | Done | Date done | Evidence kept where |
| --- | --- | --- | --- | --- | --- |
| 26 | Win the first live permanent vacancy with signed terms | Signed terms and Vacancy Brief | ☐ |  |  |
| 27 | Check temporary rates for each role in the Pricing Calculators | Rate card (not in use yet) | ☐ |  |  |
| 28 | Credit-check possible temporary clients (no supply yet) | Approved client list and limits | ☐ |  |  |
| 29 | Audit documents and systems; record it in the Audits register | Audit record | ☐ |  |  |
| 30 | Review the pipeline and set the 90-day plan | Monthly report | ☐ |  |  |

# Temporary Staffing Readiness

| Day | Action | Deliverable | Done | Date done | Evidence kept where |
| --- | --- | --- | --- | --- | --- |
| 45 | Payroll provider set up; PAYE, pension and holiday pay tested | Test payroll run | ☐ |  |  |
| 50 | Employers’ liability (at least £5 million) and temporary staffing cover in place | Certificates | ☐ |  |  |
| 55 | 13-week cash-flow forecast and funding (for example invoice finance) agreed | Forecast and facility letter | ☐ |  |  |
| 60 | Credit limits, weekly invoicing, 7-day terms and stop-supply rule agreed | Client credit file | ☐ |  |  |
| 75 | Director signs every item in the Temp Go Live Gate | Gate showing GO | ☐ |  |  |
| 90 | Pilot with 1 to 2 trusted clients, then audit after the first payroll | Pilot audit | ☐ |  |  |

# Every week

| Weekly routine | Target | Wk 1 | Wk 2 | Wk 3 | Wk 4 |
| --- | --- | --- | --- | --- | --- |
| Research target providers | 20 | ☐ | ☐ | ☐ | ☐ |
| Tailored first emails | 10 to 15 | ☐ | ☐ | ☐ | ☐ |
| Follow-up calls | 15 to 20 | ☐ | ☐ | ☐ | ☐ |
| Discovery meetings | 3 | ☐ | ☐ | ☐ | ☐ |
| Candidate screening conversations | 5 or more | ☐ | ☐ | ☐ | ☐ |
| Consented submissions (when real vacancies exist) | 2 | ☐ | ☐ | ☐ | ☐ |
| Every active record has an owner and next action | All | ☐ | ☐ | ☐ | ☐ |
| Friday review: pipeline, cash, compliance; no red item without an owner | Done | ☐ | ☐ | ☐ | ☐ |

# Every month

| Monthly check | Done | Date | Notes |
| --- | --- | --- | --- |
| Audit a sample of candidate and client files (record in Audits register) | ☐ |  |  |
| Check right to work, registration and DBS follow-up dates | ☐ |  |  |
| Review complaints, safeguarding concerns and incidents for trends | ☐ |  |  |
| Management accounts: revenue, gross profit, cash, VAT | ☐ |  |  |
| Export a backup from Haverton Operations (Data page) | ☐ |  |  |
| Review this Action Plan and add next month’s actions | ☐ |  |  |

# Every quarter

| Quarterly check | Done | Date | Notes |
| --- | --- | --- | --- |
| Check GOV.UK, ICO, Fair Work Agency and HMRC guidance for changes | ☐ |  |  |
| Review pricing, margins and client concentration | ☐ |  |  |
| Review the business plan targets against actual results | ☐ |  |  |